## Summary
DataProduct | TimeLine | ReportName | Stage | Complexity
Sales Order | FY25-Q1 | rep1 | Discovery | M
Sales Order | FY25-Q1 | rep1 | Report development | M
Sales Order | FY25-Q1 | rep1 | Testing and validation | M
Sales Order | FY25-Q1 | rep1 | Deployment | M
Sales Order | FY25-Q1 | rep1 | Post Deployment Support | M
Sales Order | FY25-Q1 | rep2 | Discovery | L
Sales Order | FY25-Q1 | rep2 | Report development | L
Sales Order | FY25-Q1 | rep2 | Testing and validation | L
Sales Order | FY25-Q1 | rep2 | Deployment | L
Sales Order | FY25-Q1 | rep2 | Post Deployment Support | L
Sales Order | FY25-Q1 | rep3 | Discovery | XL
Sales Order | FY25-Q1 | rep3 | Report development | XL
Sales Order | FY25-Q1 | rep3 | Testing and validation | XL
Sales Order | FY25-Q1 | rep3 | Deployment | XL
Sales Order | FY25-Q1 | rep3 | Post Deployment Support | XL
Sales Order | FY25-Q1 | rep4 | Discovery | S
Sales Order | FY25-Q1 | rep4 | Report development | S
Sales Order | FY25-Q1 | rep4 | Testing and validation | S
Sales Order | FY25-Q1 | rep4 | Deployment | S
Sales Order | FY25-Q1 | rep4 | Post Deployment Support | S
Bookings | FY25-Q2 | rep5 | Discovery | M
Bookings | FY25-Q2 | rep5 | Report development | M
Bookings | FY25-Q2 | rep5 | Testing and validation | M
Bookings | FY25-Q2 | rep5 | Deployment | M
Bookings | FY25-Q2 | rep5 | Post Deployment Support | M
Bookings | FY25-Q2 | rep6 | Discovery | L
Bookings | FY25-Q2 | rep6 | Report development | L
Bookings | FY25-Q2 | rep6 | Testing and validation | L
Bookings | FY25-Q2 | rep6 | Deployment | L
Bookings | FY25-Q2 | rep6 | Post Deployment Support | L
Bookings | FY25-Q2 | rep7 | Discovery | XL
Bookings | FY25-Q2 | rep7 | Report development | XL
Bookings | FY25-Q2 | rep7 | Testing and validation | XL
Bookings | FY25-Q2 | rep7 | Deployment | XL
Bookings | FY25-Q2 | rep7 | Post Deployment Support | XL
Bookings | FY25-Q2 | rep8 | Discovery | S
Bookings | FY25-Q2 | rep8 | Report development | S
Bookings | FY25-Q2 | rep8 | Testing and validation | S
Bookings | FY25-Q2 | rep8 | Deployment | S
Bookings | FY25-Q2 | rep8 | Post Deployment Support | S

## Detail-Task
DataProduct | TimeLine | ReportName | Stage | Task | parentOrChild | Complexity
Sales Order | FY25-Q1 | rep1 | Discovery | Discovery | Parent | M
Sales Order | FY25-Q1 | rep1 | Discovery | Gather and document report requirements | Child | M
Sales Order | FY25-Q1 | rep1 | Discovery | Define report scope and use cases | Child | M
Sales Order | FY25-Q1 | rep1 | Discovery | Define Metric and KPI definitions | Child | M
Sales Order | FY25-Q1 | rep1 | Discovery | Define personas and data security | Child | M
Sales Order | FY25-Q1 | rep1 | Report development | Report development | Parent | M
Sales Order | FY25-Q1 | rep1 | Report development | Design and Develop data model | Child | M
Sales Order | FY25-Q1 | rep1 | Report development | Build Framework and Reports | Child | M
Sales Order | FY25-Q1 | rep1 | Report development | Actual Development | Child | M
Sales Order | FY25-Q1 | rep1 | Report development | Implement data Security | Child | M
Sales Order | FY25-Q1 | rep1 | Report development | Optimize report performance | Child | M
Sales Order | FY25-Q1 | rep1 | Report development | Unit Tests | Child | M
Sales Order | FY25-Q1 | rep1 | Testing and validation | Testing and validation | Parent | M
Sales Order | FY25-Q1 | rep1 | Testing and validation | Perform unit testing | Child | M
Sales Order | FY25-Q1 | rep1 | Testing and validation | Data Validation | Child | M
Sales Order | FY25-Q1 | rep1 | Testing and validation | User acceptance testing (UAT) | Child | M
Sales Order | FY25-Q1 | rep1 | Deployment | Deployment | Parent | M
Sales Order | FY25-Q1 | rep1 | Deployment | Deploy product to QA environment | Child | M
Sales Order | FY25-Q1 | rep1 | Deployment | Deploy product to PROD environment | Child | M
Sales Order | FY25-Q1 | rep1 | Post Deployment Support | Post Deployment Support | Parent | M
Sales Order | FY25-Q1 | rep1 | Post Deployment Support | Monitor report performance | Child | M
Sales Order | FY25-Q1 | rep1 | Post Deployment Support | Address any issues or bugs | Child | M
Sales Order | FY25-Q1 | rep1 | Post Deployment Support | Monitor Report Adoption | Child | M
Sales Order | FY25-Q1 | rep2 | Discovery | Discovery | Parent | L
Sales Order | FY25-Q1 | rep2 | Discovery | Gather and document report requirements | Child | L
Sales Order | FY25-Q1 | rep2 | Discovery | Define report scope and use cases | Child | L
Sales Order | FY25-Q1 | rep2 | Discovery | Define Metric and KPI definitions | Child | L
Sales Order | FY25-Q1 | rep2 | Discovery | Define personas and data security | Child | L
Sales Order | FY25-Q1 | rep2 | Report development | Report development | Parent | L
Sales Order | FY25-Q1 | rep2 | Report development | Design and Develop data model | Child | L
Sales Order | FY25-Q1 | rep2 | Report development | Build Framework and Reports | Child | L
Sales Order | FY25-Q1 | rep2 | Report development | Actual Development | Child | L
Sales Order | FY25-Q1 | rep2 | Report development | Implement data Security | Child | L
Sales Order | FY25-Q1 | rep2 | Report development | Optimize report performance | Child | L
Sales Order | FY25-Q1 | rep2 | Report development | Unit Tests | Child | L
Sales Order | FY25-Q1 | rep2 | Testing and validation | Testing and validation | Parent | L
Sales Order | FY25-Q1 | rep2 | Testing and validation | Perform unit testing | Child | L
Sales Order | FY25-Q1 | rep2 | Testing and validation | Data Validation | Child | L
Sales Order | FY25-Q1 | rep2 | Testing and validation | User acceptance testing (UAT) | Child | L
Sales Order | FY25-Q1 | rep2 | Deployment | Deployment | Parent | L
Sales Order | FY25-Q1 | rep2 | Deployment | Deploy product to QA environment | Child | L
Sales Order | FY25-Q1 | rep2 | Deployment | Deploy product to PROD environment | Child | L
Sales Order | FY25-Q1 | rep2 | Post Deployment Support | Post Deployment Support | Parent | L
Sales Order | FY25-Q1 | rep2 | Post Deployment Support | Monitor report performance | Child | L
Sales Order | FY25-Q1 | rep2 | Post Deployment Support | Address any issues or bugs | Child | L
Sales Order | FY25-Q1 | rep2 | Post Deployment Support | Monitor Report Adoption | Child | L
Sales Order | FY25-Q1 | rep3 | Discovery | Discovery | Parent | XL
Sales Order | FY25-Q1 | rep3 | Discovery | Gather and document report requirements | Child | XL
Sales Order | FY25-Q1 | rep3 | Discovery | Define report scope and use cases | Child | XL
Sales Order | FY25-Q1 | rep3 | Discovery | Define Metric and KPI definitions | Child | XL
Sales Order | FY25-Q1 | rep3 | Discovery | Define personas and data security | Child | XL
Sales Order | FY25-Q1 | rep3 | Report development | Report development | Parent | XL
Sales Order | FY25-Q1 | rep3 | Report development | Design and Develop data model | Child | XL
Sales Order | FY25-Q1 | rep3 | Report development | Build Framework and Reports | Child | XL
Sales Order | FY25-Q1 | rep3 | Report development | Actual Development | Child | XL
Sales Order | FY25-Q1 | rep3 | Report development | Implement data Security | Child | XL
Sales Order | FY25-Q1 | rep3 | Report development | Optimize report performance | Child | XL
Sales Order | FY25-Q1 | rep3 | Report development | Unit Tests | Child | XL
Sales Order | FY25-Q1 | rep3 | Testing and validation | Testing and validation | Parent | XL
Sales Order | FY25-Q1 | rep3 | Testing and validation | Perform unit testing | Child | XL
Sales Order | FY25-Q1 | rep3 | Testing and validation | Data Validation | Child | XL
Sales Order | FY25-Q1 | rep3 | Testing and validation | User acceptance testing (UAT) | Child | XL
Sales Order | FY25-Q1 | rep3 | Deployment | Deployment | Parent | XL
Sales Order | FY25-Q1 | rep3 | Deployment | Deploy product to QA environment | Child | XL
Sales Order | FY25-Q1 | rep3 | Deployment | Deploy product to PROD environment | Child | XL
Sales Order | FY25-Q1 | rep3 | Post Deployment Support | Post Deployment Support | Parent | XL
Sales Order | FY25-Q1 | rep3 | Post Deployment Support | Monitor report performance | Child | XL
Sales Order | FY25-Q1 | rep3 | Post Deployment Support | Address any issues or bugs | Child | XL
Sales Order | FY25-Q1 | rep3 | Post Deployment Support | Monitor Report Adoption | Child | XL
Sales Order | FY25-Q1 | rep4 | Discovery | Discovery | Parent | S
Sales Order | FY25-Q1 | rep4 | Discovery | Gather and document report requirements | Child | S
Sales Order | FY25-Q1 | rep4 | Discovery | Define report scope and use cases | Child | S
Sales Order | FY25-Q1 | rep4 | Discovery | Define Metric and KPI definitions | Child | S
Sales Order | FY25-Q1 | rep4 | Discovery | Define personas and data security | Child | S
Sales Order | FY25-Q1 | rep4 | Report development | Report development | Parent | S
Sales Order | FY25-Q1 | rep4 | Report development | Design and Develop data model | Child | S
Sales Order | FY25-Q1 | rep4 | Report development | Build Framework and Reports | Child | S
Sales Order | FY25-Q1 | rep4 | Report development | Actual Development | Child | S
Sales Order | FY25-Q1 | rep4 | Report development | Implement data Security | Child | S
Sales Order | FY25-Q1 | rep4 | Report development | Optimize report performance | Child | S
Sales Order | FY25-Q1 | rep4 | Report development | Unit Tests | Child | S
Sales Order | FY25-Q1 | rep4 | Testing and validation | Testing and validation | Parent | S
Sales Order | FY25-Q1 | rep4 | Testing and validation | Perform unit testing | Child | S
Sales Order | FY25-Q1 | rep4 | Testing and validation | Data Validation | Child | S
Sales Order | FY25-Q1 | rep4 | Testing and validation | User acceptance testing (UAT) | Child | S
Sales Order | FY25-Q1 | rep4 | Deployment | Deployment | Parent | S
Sales Order | FY25-Q1 | rep4 | Deployment | Deploy product to QA environment | Child | S
Sales Order | FY25-Q1 | rep4 | Deployment | Deploy product to PROD environment | Child | S
Sales Order | FY25-Q1 | rep4 | Post Deployment Support | Post Deployment Support | Parent | S
Sales Order | FY25-Q1 | rep4 | Post Deployment Support | Monitor report performance | Child | S
Sales Order | FY25-Q1 | rep4 | Post Deployment Support | Address any issues or bugs | Child | S
Sales Order | FY25-Q1 | rep4 | Post Deployment Support | Monitor Report Adoption | Child | S
Bookings | FY25-Q2 | rep5 | Discovery | Discovery | Parent | M
Bookings | FY25-Q2 | rep5 | Discovery | Gather and document report requirements | Child | M
Bookings | FY25-Q2 | rep5 | Discovery | Define report scope and use cases | Child | M
Bookings | FY25-Q2 | rep5 | Discovery | Define Metric and KPI definitions | Child | M
Bookings | FY25-Q2 | rep5 | Discovery | Define personas and data security | Child | M
Bookings | FY25-Q2 | rep5 | Report development | Report development | Parent | M
Bookings | FY25-Q2 | rep5 | Report development | Design and Develop data model | Child | M
Bookings | FY25-Q2 | rep5 | Report development | Build Framework and Reports | Child | M
Bookings | FY25-Q2 | rep5 | Report development | Actual Development | Child | M
Bookings | FY25-Q2 | rep5 | Report development | Implement data Security | Child | M
Bookings | FY25-Q2 | rep5 | Report development | Optimize report performance | Child | M
Bookings | FY25-Q2 | rep5 | Report development | Unit Tests | Child | M
Bookings | FY25-Q2 | rep5 | Testing and validation | Testing and validation | Parent | M
Bookings | FY25-Q2 | rep5 | Testing and validation | Perform unit testing | Child | M
Bookings | FY25-Q2 | rep5 | Testing and validation | Data Validation | Child | M
Bookings | FY25-Q2 | rep5 | Testing and validation | User acceptance testing (UAT) | Child | M
Bookings | FY25-Q2 | rep5 | Deployment | Deployment | Parent | M
Bookings | FY25-Q2 | rep5 | Deployment | Deploy product to QA environment | Child | M
Bookings | FY25-Q2 | rep5 | Deployment | Deploy product to PROD environment | Child | M
Bookings | FY25-Q2 | rep5 | Post Deployment Support | Post Deployment Support | Parent | M
Bookings | FY25-Q2 | rep5 | Post Deployment Support | Monitor report performance | Child | M
Bookings | FY25-Q2 | rep5 | Post Deployment Support | Address any issues or bugs | Child | M
Bookings | FY25-Q2 | rep5 | Post Deployment Support | Monitor Report Adoption | Child | M
Bookings | FY25-Q2 | rep6 | Discovery | Discovery | Parent | L
Bookings | FY25-Q2 | rep6 | Discovery | Gather and document report requirements | Child | L
Bookings | FY25-Q2 | rep6 | Discovery | Define report scope and use cases | Child | L
Bookings | FY25-Q2 | rep6 | Discovery | Define Metric and KPI definitions | Child | L
Bookings | FY25-Q2 | rep6 | Discovery | Define personas and data security | Child | L
Bookings | FY25-Q2 | rep6 | Report development | Report development | Parent | L
Bookings | FY25-Q2 | rep6 | Report development | Design and Develop data model | Child | L
Bookings | FY25-Q2 | rep6 | Report development | Build Framework and Reports | Child | L
Bookings | FY25-Q2 | rep6 | Report development | Actual Development | Child | L
Bookings | FY25-Q2 | rep6 | Report development | Implement data Security | Child | L
Bookings | FY25-Q2 | rep6 | Report development | Optimize report performance | Child | L
Bookings | FY25-Q2 | rep6 | Report development | Unit Tests | Child | L
Bookings | FY25-Q2 | rep6 | Testing and validation | Testing and validation | Parent | L
Bookings | FY25-Q2 | rep6 | Testing and validation | Perform unit testing | Child | L
Bookings | FY25-Q2 | rep6 | Testing and validation | Data Validation | Child | L
Bookings | FY25-Q2 | rep6 | Testing and validation | User acceptance testing (UAT) | Child | L
Bookings | FY25-Q2 | rep6 | Deployment | Deployment | Parent | L
Bookings | FY25-Q2 | rep6 | Deployment | Deploy product to QA environment | Child | L
Bookings | FY25-Q2 | rep6 | Deployment | Deploy product to PROD environment | Child | L
Bookings | FY25-Q2 | rep6 | Post Deployment Support | Post Deployment Support | Parent | L
Bookings | FY25-Q2 | rep6 | Post Deployment Support | Monitor report performance | Child | L
Bookings | FY25-Q2 | rep6 | Post Deployment Support | Address any issues or bugs | Child | L
Bookings | FY25-Q2 | rep6 | Post Deployment Support | Monitor Report Adoption | Child | L
Bookings | FY25-Q2 | rep7 | Discovery | Discovery | Parent | XL
Bookings | FY25-Q2 | rep7 | Discovery | Gather and document report requirements | Child | XL
Bookings | FY25-Q2 | rep7 | Discovery | Define report scope and use cases | Child | XL
Bookings | FY25-Q2 | rep7 | Discovery | Define Metric and KPI definitions | Child | XL
Bookings | FY25-Q2 | rep7 | Discovery | Define personas and data security | Child | XL
Bookings | FY25-Q2 | rep7 | Report development | Report development | Parent | XL
Bookings | FY25-Q2 | rep7 | Report development | Design and Develop data model | Child | XL
Bookings | FY25-Q2 | rep7 | Report development | Build Framework and Reports | Child | XL
Bookings | FY25-Q2 | rep7 | Report development | Actual Development | Child | XL
Bookings | FY25-Q2 | rep7 | Report development | Implement data Security | Child | XL
Bookings | FY25-Q2 | rep7 | Report development | Optimize report performance | Child | XL
Bookings | FY25-Q2 | rep7 | Report development | Unit Tests | Child | XL
Bookings | FY25-Q2 | rep7 | Testing and validation | Testing and validation | Parent | XL
Bookings | FY25-Q2 | rep7 | Testing and validation | Perform unit testing | Child | XL
Bookings | FY25-Q2 | rep7 | Testing and validation | Data Validation | Child | XL
Bookings | FY25-Q2 | rep7 | Testing and validation | User acceptance testing (UAT) | Child | XL
Bookings | FY25-Q2 | rep7 | Deployment | Deployment | Parent | XL
Bookings | FY25-Q2 | rep7 | Deployment | Deploy product to QA environment | Child | XL
Bookings | FY25-Q2 | rep7 | Deployment | Deploy product to PROD environment | Child | XL
Bookings | FY25-Q2 | rep7 | Post Deployment Support | Post Deployment Support | Parent | XL
Bookings | FY25-Q2 | rep7 | Post Deployment Support | Monitor report performance | Child | XL
Bookings | FY25-Q2 | rep7 | Post Deployment Support | Address any issues or bugs | Child | XL
Bookings | FY25-Q2 | rep7 | Post Deployment Support | Monitor Report Adoption | Child | XL
Bookings | FY25-Q2 | rep8 | Discovery | Discovery | Parent | S
Bookings | FY25-Q2 | rep8 | Discovery | Gather and document report requirements | Child | S
Bookings | FY25-Q2 | rep8 | Discovery | Define report scope and use cases | Child | S
Bookings | FY25-Q2 | rep8 | Discovery | Define Metric and KPI definitions | Child | S
Bookings | FY25-Q2 | rep8 | Discovery | Define personas and data security | Child | S
Bookings | FY25-Q2 | rep8 | Report development | Report development | Parent | S
Bookings | FY25-Q2 | rep8 | Report development | Design and Develop data model | Child | S
Bookings | FY25-Q2 | rep8 | Report development | Build Framework and Reports | Child | S
Bookings | FY25-Q2 | rep8 | Report development | Actual Development | Child | S
Bookings | FY25-Q2 | rep8 | Report development | Implement data Security | Child | S
Bookings | FY25-Q2 | rep8 | Report development | Optimize report performance | Child | S
Bookings | FY25-Q2 | rep8 | Report development | Unit Tests | Child | S
Bookings | FY25-Q2 | rep8 | Testing and validation | Testing and validation | Parent | S
Bookings | FY25-Q2 | rep8 | Testing and validation | Perform unit testing | Child | S
Bookings | FY25-Q2 | rep8 | Testing and validation | Data Validation | Child | S
Bookings | FY25-Q2 | rep8 | Testing and validation | User acceptance testing (UAT) | Child | S
Bookings | FY25-Q2 | rep8 | Deployment | Deployment | Parent | S
Bookings | FY25-Q2 | rep8 | Deployment | Deploy product to QA environment | Child | S
Bookings | FY25-Q2 | rep8 | Deployment | Deploy product to PROD environment | Child | S
Bookings | FY25-Q2 | rep8 | Post Deployment Support | Post Deployment Support | Parent | S
Bookings | FY25-Q2 | rep8 | Post Deployment Support | Monitor report performance | Child | S
Bookings | FY25-Q2 | rep8 | Post Deployment Support | Address any issues or bugs | Child | S
Bookings | FY25-Q2 | rep8 | Post Deployment Support | Monitor Report Adoption | Child | S